# Inverclyde Tourism Strategy

# 2009-2016

# Mid Term Review

### Overview of the Inverclyde Tourism Economy

The Inverclyde Tourism Strategy & Action Plan was developed in 2009 after consultation with all interested parties involved in the delivery of services to visitors to the Inverclyde area and also public sector parties such as Visit Scotland and agencies such as Greenock Chamber of Commerce and Discover Inverclyde. The strategy aims to promote the positive aspects of the area to allow them to contribute and participate in the development of tourism and provide a sound economic future for the area through the implementation of the action plan.

It is now 3 years since the action plan began and the world economic climate has changed significantly resulting in a realization that optimistic targets and forecasts for growth have not been achieved. We are now experiencing a double dip recession in the UK and targets set by the Scottish Government for a 50% revenue growth in tourism by 2015 have proved to be unrealistic although Scotland’s tourism industry has maintained its position as a key contributor to the nation’s economy generating an annual visitor spend in excess of £4.5bn.

Despite the recession, evidence from the Scottish Tourism Economic Activity Monitor (STEAM) would appear to indicate that since 2009, revenue from urban tourism activity in Inverclyde has increased year on year from £26.81m in 2009 to £32.41m in 2011 showing an increase of 21% with rural tourism in Inverclyde showing an even bigger improvement of 25% over the period.

Further detailed analysis below shows that employment supported by tourism activity has generally increased over the period (except for the accommodation sector) demonstrating that tourism is increasingly becoming more important to the Inverclyde economy.

Accommodation			-0.7%

Food & Drink			+8.8%

Recreation			+7.5%

Shopping 			+10%

Transport 			+9.8%

### The New Strategic Context

A new Tourism Strategy for Scotland (Tourism Scotland 2020) has been developed over the last two years by a steering group drawn from the Tourism Leadership Group and the Tourism Alliance and was published in June 2012. The new strategy aims to ensure that it will be industry led and will make Scotland a destination of first choice for a high quality, value for money and memorable customer experience, delivered by skilled and passionate people.

Tourism is recognised as one of Scotland’s key economic contributors with day visitors contributing £6.2bn and overnight visitors generating in excess of £4.5bn annually. Tourism accounts for over 200,000 jobs across 20,000 tourism related businesses whilst also feeding into other sectors such as food and drink, retail, transport and construction.

The new Scottish Tourism Strategy will focus on turning 4 groups of tourism assets into quality, authentic visitor experiences.

- Nature, heritage and activities

- Destination towns and cities

- Events & festivals

- Business tourism

The ambition of the new national strategy is to achieve an annual overnight visitor spend of between £5.5bn and £6.5bn by 2020 for the whole of Scotland which translates to an additional £1bn or 18% growth.

Market analysis has identified that particular Scottish assets offer significant growth potential especially in areas such as Inverclyde where tourism is aspiring to become a mainstay within the economy and businesses and industry groups need to work together more effectively to develop this sector for the future.

Potential Areas for Growth (Source: The Tourism Scotland 2020 National Strategy)

Activities & adventure		+ £89m by 2015

Cruise			   + 1.1m visitors by 2029

Golf			+10%-53% over 10 years

Mountain biking		+£36m by 2015

Sailing			+£44m by 2020

In future, the main measures of success in terms of Tourism development will be calculated in terms of overnight visitor spend and visitor satisfaction and the Tourism Alliance will put in place mechanisms to ensure that information is gathered on a consistent and comprehensive basis capturing day visitor numbers.

### What next for the Inverclyde Tourism Strategy and Action Plan?

Following consultation with our partners,

- Local Area Tourism Partnership

- Discover Inverclyde

- Greenock Chamber of Commerce

- Inverclyde Council (across services)

- Scottish Enterprise

- VisitScotland

- Sail Scotland

- Clydeport

- EventScotland

- Inverclyde Leisure

- Scottish Natural Heritage

- Clyde Muirshiel Regional Park

- Historic Scotland

- Riverside Inverclyde

- The Inverclyde Alliance

- The Inverclyde Tourist Group

- The Inverclyde Community Development Trust

- Caledonian Macbrayne

- Western Ferries

…and input from the Inverclyde Local Area Tourism Partnership group, the aims and objectives of the Inverclyde Tourism Strategy & Action Plan 2009-16 have been reviewed and aligned with the new Tourism Scotland 2020 Strategy for the remaining 3 years of our plan to ensure that Inverclyde tourism businesses and partner agencies are all working towards a Scotland that is a destination of first choice for a high quality, value for money and memorable customer experience, delivered by skilled and passionate people.

Additionally, a list of new Baseline Indicators have been included at the end of this mid term review in order to be able to more clearly evaluate the progress of the Strategy over the remaining 3 years and also focus activity on some identifiable, achievable targets that can demonstrate progress with regard to development of the tourism sector as an economic driver for the future of the Inverclyde economy.

Our shared vision for Inverclyde is to achieve sustainable growth for the tourism sector and to maximize the contribution that the tourism sector makes to the Inverclyde economy particularly through the day visitor and short leisure break market. The increasing number of cruise ships that visit the Ocean Terminal in Greenock each year bringing thousands of day visitors together with the potential of developing packages of our natural assets and heritage, are creating real opportunities for the development of existing and the creation of new tourism and hospitality businesses and the revised strategy and action plan seeks to deliver real sustainable change by 2016.

# Inverclyde Tourism Action Plan 2013 - 2016

# The new themes for action (in line with the new National Tourism Strategy) are as follows:-

Theme 1 	Knowing our markets

Theme 2	Managing the customer journey

Theme 3	Building sustainable tourism

Theme 4	Strengthening leadership and collaboration

Theme 5	Better data

## The organisations who will assist in the delivery of the plan:-

DI 	Discover Inverclyde

CMRP 	Clyde Muirshiel Regional Park

EV 	Event Scotland

FSB 	Federation of Small Businesses

GCC 	Greenock Chamber of Commerce

IEDT	 Inverclyde Events Development Team

IC 	Inverclyde Council

IL 	Inverclyde Leisure

ITG 	Inverclyde Tourist Group

LATP 	Local Area Tourism Partnership

RI 	Riverside Inverclyde

PS	Private sector

SDS 	Skills Development Scotland

SCDI 	Scottish Council for Development & Industry

SG	Scottish Government

VS 	Visit Scotland

Theme 1

To better know our markets by providing better data

| Key Objectives/Aspirations | Actions | Lead | Partners | Outputs/Outcomes | Target year |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2013 | 2014 | 2015 |
| 1) Know our customers | - Establish a local annual data gathering exercise through a standard short questionnaire which can be issued to all tourism/hospitality businesses to use with their visitors. Standard 5 questions paper and online | IC/LATP | LATP, FSB, ITG, DI, GCC + DIWaters | Utilise STEAM/DREAM economic impact stats more effectively and disseminate. Standardised q’aire to be developed for va’s and accom providers | * | * | * |
|  | - Carry out a visitor survey in 2013 across Inverclyde to find out who our visitors are, where they come from, how much they spend, where they visit in Inverclyde and what they would like to see in the future | IC | External consultants | Completed. | * |  |  |
| 2) Use market intelligence more effectively | - Source and gather existing local info and collate & share with all Inverclyde tourism/hospitality businesses to use in their business development eg Oak Mall, Clydeport, Funworld, McLean Museum, Beacon Arts Theatre, Clyde Muirshiel | IC, LATP | LATP members, DI, ITG | Encourage all tourism businesses to supply stats to the annual Occupancy Survey and Visitor Attraction Monitor. Increase participation by 10% year on year. |  | * |  |
|  | - Disseminate national and local tourism intelligence information amongst local tourism businesses to assist them in future development | IC | LATP/DI/ DIW | Emails with links to share with LATP members and ITG to share their annual reviews. | * |  |  |
| 3) Identify potential growth markets and develop products and services accordingly | - Explore development of new products and services around assets and experiences eg sailing, marine, heritage, golf, cycling | IC,VS, LATP | SE, VS, IC, LATP, DI | Development of new partnership packages/offers each year – eat/sail/golf/heritage walks | * | * | * |
|  | - Work in partnership to encourage more cruise ships to come to Greenock. Encourage businesses and traders to embrace the opportunity and develop their businesses to provide services and products that additional visitors want | Clydeport | ITG, IC, VS, FSB, GCC, RI | Increased number of cruise ships coming to Greenock by the development of Terminal 2 (City deal).. Development of an annual Inverclyde Tourism Conference | * | * | * |
|  | - Make contact with cruise ship tour organisers to establish what additional local tours/activities they might like to see developed to offer for passengers alighting at Greenock on future cruises eg sail charters on the Clyde | IC, LATP | ITG, DI, Clydeport | Annual ITG visitor survey of cruise ship passengers and share with local tourism businesses. |  | * |  |

Theme 2

To manage the customer journey

| Key Objectives/Aspirations | Actions | Lead | Partners | Outputs/Outcomes | Target year |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2013 | 2014 | 2015 |
| 1) Develop tourism assets into authentic experiences | - Work together to develop and promote new Inverclyde facilities/attractions eg The Beacon, Fire Brigade Museum, Clyde Muirshiel Regional Park, golf & stay, walk & stay and water & sailing activities | IC/DI | LATP members, DI | Annual advertising/ area promotional campaigns. New packages developed. Promotion posters in key stations in Inverclyde and attractions to encourage longer stays in area | * | * | * |
|  | - Work in partnership to deliver the first Heritage Inverclyde project - the coastal trail | HI Steering Group | LATP, IC, DI | Launch in October 2014 + link to Clyde Coastal Trail. |  | * |  |
|  | - Further work together to develop new packages to turn assets into experiences and investigate potential growth for Inverclyde in the development of business tourism offers. | LATP/ RI | DI, VS, SE, ITG | See Theme 1 3)I Work with Place Partnership Project and Creative Scotland. | * | * | * |
|  | - Encourage partnership working with the Living Inverclyde campaign to develop a local Inverclyde Ambassadors scheme for all ages and a celebration award to recognise success in tourism and customer care. | IC/DI/ ITG | The Trust, LATP members | Develop annual Inverclyde Tourism/hospitality awards project and event. |  | * |  |
|  | - Work in partnership with public and private organisations who run events in Inverclyde, to develop existing and create new, events and festivals in the area to attract significantly large numbers visitors | IC/IEDT/LATP/RI | VS, ES, DI, PS | A single Inverclyde event calendar. Development of an annual Inverclyde tourism/hospitality awards event |  | * | * |
|  | - Encourage, develop and promote the availability of the quality open/green space provision in Inverclyde including the network of safe cycle, walking and horse riding routes and the potential for the development of a range of water and land based activities | IC, CMRP | LATP, GCC, DI, IL, RI | Develop cycle/walking/horse riding routes and packages for marine tourism Feasibility study for more water access points and attract more providers. | * | * | * |
|  | - Ensuring active Inverclyde promotion via national online marketing and a presence in printed publications | IC, LATP, VS | DI | Annual schedule of activity | * | * | * |
| 2) Develop a high quality visitor experience | - Explore options for the provision of additional Visit Scotland Information provision in Greenock within an existing facility. | IC, VS | LATP, ITG, IL | Potential additional ummanned info point at Customhouse.Develop project with RI and Wylie Foundation |  | * |  |
|  | - Conduct research to find out training needs for Inverclyde tourism/hospitality businesses and organise appropriate training sessions | IC | LATP/DI | 2 training sessions for tourism businesses annually plus online Welcomes explore |  | * |  |
|  | - Offer nationally recognised customer care training for all Inverclyde tourism/hospitality businesses to raise quality standard | IC,VS | LATP | Identify and engage with a supplier to deliver at least 2 customer care training sessions pa | * |  |  |
|  | - Further develop Discover Inverclyde as the one stop agency to provide access to all information about the area for potential visitors | ALL | All | The creation of a DMO |  |  | * |
|  | - Encourage the aspiration to bring a 4* hotel /conference venue development to Inverclyde | IC, LATP, VS, RI | SCDI, Business Gateway | A new hotel in Inverclyde |  |  | * |
|  | - Explore potential and establish appropriate social media platforms via Discover Inverclyde to interact with visitors and promote all that is on offer | DI | All | Establish active Twitter, Facebook, You Tube | * | * | * |
|  | - Improve public realm areas and built environment including cleanliness in both urban and rural areas eg signage improvements, development of trails, greening of derelict sites, regular tidy ups of roadsides, paths and public areas | IC | ITG, DI, RI LATP | New /replacement/removal of signage, development of town & heritage trails, public realm maintenance programme to improve visitor experience | * | * | * |
|  | - Encourage and assist tourism businesses to consider submitting bids for national awards such as the Scottish Thistle Awards in recognition of the achievements of local businesses | LATP, PS | IC, VS | Inverclyde businesses assisted to submit bids. | * | * | * |
|  | - Work in partnership to improve the quality and variety of retail offering in our town centres to increase visitors | GCC, RI | DI, IC,LATP, FSB | Scheduled plan to make improvements to streetscapes/tourism signage in all towns and villages | * | * | * |
|  | - Encourage the development of e-business capability of all the tourism/hospitality businesses in Inverclyde | IC, DI, RI | LATP, FSB, GCC | All tourism/hospitality businesses to have a company email, web presence (website, social media) | * | * | * |
| 3) Improve QA star gradings for tourism/hospitality businesses | - Encourage all Inverclyde businesses to be part of the Visit Scotland QA or food & drink schemes | IC, VS | LATP, DI members, RI | Number of businesses per annum joining QA via financial assistance from IC | * | * | * |
|  | - Encourage tourism/hospitality businesses to invest in new facilities/improvements through take up of Business Development Assistance options | IC | LATP, DI members | At least 20 assists/interventions per annum | * | * | * |

Theme 3

To build sustainable tourism – economic, environmental and social growth

|  | Key Objectives/Aspirations |  | Actions |  | Lead |  |  | Partners |  | Outputs/outcomes |  |  |  | Target year |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  | 2013 |  |  |  | 2014 |  | 2015 |  |
|  | 1) Build a more sustainable industry |  | - Encourage tourism/hospitality businesses to join the national Green Tourism Business Scheme |  | IC, VS |  |  | LATP, DI members/ ITG |  | An additional 2 businesses to be members by 2016. |  |  |  |  |  |  |  |  | * |  |
|  |  |  | - Identify and work with existing "sustainable" businesses such as CMRP to encourage them in their aspirations to bring more visitors to the area by developing more sustainable facilities and activities |  | IC, CMRP |  |  | LATP, ITG, VS |  | Increased visitor numbers |  |  | * |  |  |  | * |  | * |  |
|  |  |  | - Raise the profile of tourism in Inverclyde itself through positive stories and images in the local press |  | IC/LATP |  |  | DI, GCC, ITG, Clydeport, The Trust |  | Press releases generated and column inches/appearances in Greenock Telegraph/Inverclyde Now. More social media activity including blogging, tweeting and Facebook. |  |  | * |  |  |  | * |  | * |  |
|  | 2) Improve frequency and variety of public transport |  | - Partnership to encourage the frequency and reliability of public transport options with suppliers and also encourage more information on how, where and when visitors can access them |  | GCC, FSB, ITG, PS, DI |  |  | LATP members |  | Personalised timetables at key bus stops. Increase frequency of train service to 4 per hour. Improve/increase/replace tourism signage |  |  |  |  |  |  |  |  | * |  |
|  | 3) Encourage a greater uptake of funding for tourism/event projects |  | - Private/public sector to work together to identify potential and attract new national/international events to Inverclyde. Create funding bids for tourism/event projects and submit joint bids. |  | DI/IC |  |  | IEDT, ES, VS |  | Make bids to i) attract new large events to Inverclyde ii) ES and VS for funding to promote Inverclyde events |  |  |  |  |  |  | * |  |  |  |
|  |  |  | - Continue to invest in business development through tourism grants and external funding |  | IC |  |  | PS, LATP, DI members |  | 20 tourism business assists per annum |  |  | * |  |  |  | * |  | * |  |
|  | 4) Seek more efficient practices that benefit business, communities and environment |  | - Seek advice from Visit Scotland re options for training/information sessions for local businesses on ways to become more sustainable |  | LATP |  |  | PS tourism business |  | Training schedule for the next 3 years to be arranged |  |  | * |  |  |  |  |  |  |  |
|  |  |  | - Encourage tourism/hospitality businesses to get involved with local green initiatives such as the Inverclyde Cleaner, Greener, Safer and Stronger initiative and buy in to the Council Green Charter by finding out more info |  | LATP |  |  | LATP, DI members |  | Invitation to green initiatives to supply speakers to present to LATP/DI. |  |  |  |  |  |  |  |  | * |  |
|  |  |  | - Seek to work with more social economy organisations, community groups and schools to develop opportunities for residents to acquire skills and knowledge and become involved in providing services to visitors |  | IC |  | ITG, The Trust, Heritage Inverclyde Steering group organisations |  |  |  | Develop training programme and create opportunities for self employment, new private sector, social economy organisations to deliver more tourism services eg info guides, cycle hire, activity packages |  |  |  |  |  | * |  |  |  |
|  |  | - Continue to ensure that the importance of Tourism development is recognised by all Alliance partners and included in all relevant local strategy plans |  | IC |  | All |  |  | Reference to tourism development in all area economic development strategies and plans.Seek representation on sub group of the Alliance. |  |  | * |  |  |  | * |  | * |  |  |
| 5) Achieve the full potential from tourism/hospitality throughout the year. |  | - Identify ideas to build tourism/hospitality business throughout the year not just during the summer season |  | IEDT/ LATP, RI |  | VS, IC, FSB, ITG, GCC |  |  | Development of more day visitor events throughout the year eg Christmas market, food/wildlife/sailing festivals and more opportunities for Inverclyde businesses to cross sell |  |  |  |  |  |  |  |  | * |  |  |
|  |  | - Recognise the natural assets of the area and work together to create partnership packages linking experience, food & drink, transportation and accommodation |  | IC |  | VS, DI, LATP, PS |  |  | See theme 1 3)i |  |  | * |  |  |  | * |  | * |  |  |
|  |  | - Encourage more of our young people into tourism related training and employment by encouraging tourism businesses to grow or encourage more start up tourism businesses |  | SDS, IC |  | ITG, The Trust, IC, SDS, DI |  |  | Encourage more business start ups and job creation in hospitality/tourism sector via mentoring and placements, Employability fund, ICDT volunteers in schools. |  |  | * |  |  |  | * |  | * |  |  |
|  |  | - Working in partnership undertake a Visit Scotland area promotional media campaign |  | IC |  | VS, LATP (hospitality/ food members |  |  | IC to fund a 2013 promotional campaign for day visitors focussing on an Inverclyde food offer |  |  | * |  |  |  | * |  | * |  |  |
|  |  | - Working with partners to develop arts/sports/heritage projects/events to utilise existing sites and facilities to attract visitors and potentially create legacy projects for the future |  | RI/IEDT |  | IL, IC, DI |  |  | Maximise use of all Inverclyde leisure sites and facilities during 2014. Utilise assets such as Sugar Sheds more |  |  |  |  |  |  | * |  |  |  |  |
|  |  | - Partners to be encouraged to promote their services on the Discover Inverclyde stand at the annual Tourism Expo event in May to promote packages/activities available in Inverclyde |  | LATP/DI |  | DI, LATP members |  |  | Annual stand at Expo with 3 DI businesses exhibiting Inverclyde packages and products |  |  | * |  |  |  | * |  | * |  |  |

.Theme 4

To strengthen leadership and collaboration

| Key Objectives/Aspirations | Actions | Lead | Partners | Outputs/outcomes | Target year |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2013 | 2014 | 2015 |
| 1) Develop capabilities and capacity of leaders in tourism businesses in Inverclyde | - Further develop and strengthen Discover Inverclyde to allow it to become the single brand for the promotion and marketing of Inverclyde to attract visitors | GRAIL/LAG | GCC, FSB, PS, DI | Develop a Greater Renfrewshires & Inverclyde Tourism BID and a bid for LEADER funding. |  |  | * |
|  | - Organise training events for business leaders to support them to take on more responsibility for area tourism development and promotion activity within Discover Inverclyde | DI, IC, RI | SDS, LATP, DI members, VS | Customer care raining events x 2 pa Online/social Media training events x1 pa | * | * | * |
| 2) Develop and strengthen partnerships between public and private sector | - Work together to create a process to attract large tourism/events projects for the remaining Winning Years and beyond eg develop an Inverclyde events programme during Year of Homecoming and promote via a joint online “Whats on” for Inverclyde | LATP | All | Work together to create new large scale events for Inverclyde that will attract more day visitors and bid for external VS Growth funding for events during the winning years eg 2015 Year of Food & Drink |  | * |  |
|  | - Investigate potential for a “Buy Local” campaign in Inverclyde | GCC, IC, DI | FSB | Buy Local promotional campaign | * | * | * |

Theme 5

To provide better data

| Key Objectives/Aspirations | Actions | Lead | Partners | Outputs/Outcomes | Target year |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2013 | 2014 | 2015 |
| 1) Improve the accuracy, reach and relevance of data sources available for businesses | - Disseminate national and local statistical information to all partners to inform decision making process | IC | National stats bodies, LATP, DI members | Regular reporting of relevant national and local statistical information shared with all interested parties |  |  | * |
|  | - Encourage representation/attendance at relevant tourism development conferences/briefing seminars on behalf of the partner businesses and disseminate information | IC | ITG, LATP, DI | Regular Inverclyde representation at national events with information disseminated to all local partners | * | * | * |
| 2) Address gaps in local knowledge | - Create a new Inverclyde annual survey of all tourism and hospitality businesses and disseminate to participants | IC | All | Annual Local Data Monitor established |  | * |  |
|  | - Explore costs of engaging an organisation to gather information from event organisers all over Inverclyde for a local “What’s On Inverclyde” website | IC (IEDT) | All | A ‘Whats on Inverclyde’ events guide established |  | * |  |
|  | - Encourage all tourism/hospitality businesses to join DI to create a comprehensive dataset of service providers for the area so that more partnership working and sharing of information can be encouraged | DI | PS | All Inverclyde tourism/hospitality businesses will be members of Discover Inverclyde |  | * | * |

BASELINE INDICATORS

| Indicator | Description | Current Source | Baseline 2011/12 | Annual Growth Rate | Target for 2015/16 |
| --- | --- | --- | --- | --- | --- |
| Total Revenue | Total spend generated by visitors to Inverclyde | STEAM | 51.74 (£’s millions) | 2% | 52.77(£’s millions) |
| Tourist Days | Number of visitors staying in Inverclyde | STEAM | 760.17 (‘000’s) | 3% | 782.97(000’s) |
| Day Visitor numbers | Number of visitors to Inverclyde | STEAM | 331.47 (000’s) | 2% | 338.09 (000’s) |
| Total employment | Number of FTE employees in tourism sector | STEAM | 973 (FTE’s) | 3% | 1002 (FTE’s) |
| Number of Quality Assurance Scheme members | Number of tourism businesses signed up to QA schemes | VisitScotland/Eat Scotland | VS QA - 9 Eat Scotland - 0 | 3% | VS 10 ES 2 |
| Increase in number of tourism/hospitality businesses | Total number of tourism/hospitality businesses in Inverclyde | Discover Inverclyde Membership | 100 | 2% | 102 |
| Number of experience “packages” developed | Number of packages developed and marketed | Local data monitor | n/a | 1 per annum | 4 |
| Number of visitor attractions | Number of visitor attractions in Inverclyde | Scottish Visitor Attraction Monitor | 4 | 3% | 5 |
| Visitor numbers to visitor attractions | Numbers of visitors to Inverclyde attractions | Scottish Visitor Attraction Monitor | 115.5 (000’s) | 3% | 119 (000’s) |
| Number of green tourism business scheme members | Number of tourism businesses signed up to Green Tourism QA schemes | VisitScotland | 2 | 2% | 3 |

BASELINE INDICATORS (updated 20/01/14)

| Indicator | Description | Current Source | Performance 2010/11 | Performance 2011/12 | Performance 2012/13 | Target 2013/14 | Target 2014/15 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total Revenue | Total spend generated by visitors to Inverclyde | STEAM/DREAM (Dream from 2013) | £48.16M | £48.01M |  | £50M | 52.77(£’s millions) |
| Tourist Days | Number of visitors staying in Inverclyde | STEAM/DREAM (Dream from 2013) | 1041.88 (000’s) | 1022.18 (000’s) |  | 1060 | 1100 (000’s) |
| Day Visitor numbers | Number of visitors to Inverclyde | STEAM/DREAM (Dream from 2013) | 503.63 (000’s) | 494.46 (000’s) |  | 503 | 550 (000’s) |
| Total employment | Number of FTE employees in tourism sector | STEAM/DREAM (Dream from 2013) | 894 | 859 |  | 890 | 900(FTE’s) |
| Number of Quality Assurance Scheme members | Number of tourism businesses signed up to QA schemes | VisitScotland/Eat Scotland | VS - 4 ES - 2 | VS - 5 ES - 3 | VS - 6 ES - 4 | VS - 7 TOB - 5 | VS 10 ES 2 |
| Increase in number of tourism/hospitality businesses | Total number of tourism/hospitality businesses in Inverclyde | Discover Inverclyde Membership | 100 | 90 | 92 | 94 | 102 |
| Number of experience “packages” developed | Number of packages developed and marketed | Local data monitor | 0 | 1 | 2 | 3 | 4 |
| Number of visitor attractions | Number of visitor attractions in Inverclyde | Scottish Visitor Attraction Monitor | 4 | 5 | 5 | 6 | 7 |
| Visitor numbers to visitor attractions | Numbers of visitors to Inverclyde attractions | Scottish Visitor Attraction Monitor | 115 (000’s) | 128 (000’s) | 130 (000’s) | 135 (000’s) | 140 (000’s) |
| Number of green tourism business scheme members | Number of tourism businesses signed up to Green Tourism QA schemes | VisitScotland | 1 | 1 | 1 | 1 | 2 |